## Risk Register
Risk ID | Risk Category | Risk Description | Business Impact | Likelihood (1-5) | Impact (1-5) | Risk Score | Current Controls | Mitigation Plan | Risk Owner | Status | Target Date | Framework Mapping
R-001 | Access Control | Excessive user permissions could allow unauthorized access to sensitive systems. | High | 4 | 5 | 20 | Quarterly RBAC reviews, MFA | Implement automated access reviews and remove dormant accounts. | IAM Manager | Open | 2026-09-30 | NIST PR.AC / CIS 6 / SOC 2 CC6
R-002 | Patch Management | Critical servers may not receive security updates on time. | High | 3 | 5 | 15 | Monthly patch cycle | Deploy automated patch management and validate compliance. | IT Operations | In Progress | 2026-08-31 | NIST PR.IP / CIS 7
R-003 | Phishing | Employees may fall victim to phishing emails. | Medium | 4 | 4 | 16 | Email filtering, MFA | Conduct quarterly awareness training and phishing simulations. | Security Awareness Lead | Open | 2026-10-15 | NIST PR.AT / CIS 14
R-004 | Vendor Risk | Third-party vendor lacks documented security controls. | High | 3 | 4 | 12 | Vendor questionnaires | Implement annual vendor risk assessments and contract security clauses. | Vendor Manager | Open | 2026-11-01 | SOC 2 CC9 / NIST ID.SC
R-005 | Backup & Recovery | Backups may fail or be unrecoverable during an incident. | High | 2 | 5 | 10 | Daily backups | Perform quarterly restore testing and document recovery procedures. | Infrastructure Manager | In Progress | 2026-08-15 | NIST PR.IP-4 / CIS 11
R-006 | Endpoint Security | Endpoints may be missing EDR protection. | High | 3 | 4 | 12 | AV installed | Deploy EDR to all managed endpoints and monitor coverage. | Endpoint Admin | Open | 2026-09-15 | NIST DE.CM / CIS 10
R-007 | Policy Compliance | Security policies are outdated and not reviewed annually. | Medium | 2 | 3 | 6 | Existing policy library | Establish annual review schedule with executive approval. | GRC Analyst | Open | 2026-12-01 | NIST GV / SOC 2 CC1
R-008 | Business Continuity | No documented disaster recovery test within past year. | High | 2 | 5 | 10 | BCP documented | Conduct annual DR exercise and update lessons learned. | Business Continuity Manager | Planned | 2026-11-30 | NIST RC / ISO 22301